## Slide 1: zDevOps PoC/Pilot (company name)
Discovery & Design Workshop
Comp? – tbd
IBM z DevOps Acceleration Team (DAT) - Nelson Lopez
IBM System Z Client Architect – TBD
IT Specialist - TBD
Notes: 3 sessions spread across the engagement
Session 1 - Current-state and Goals ( 90 Mins)
Session 2 – DBB/DevOps Overview (E2E Deck – 60-90mins)
Session 3 – End State overview (presented in a “Finding Doc” toward to end of the engagement)

## Slide 2: Discovery &Design workshop – Goals
Where you are today (SDLC on mainframe and distributed)
What are your pain points & Goals
Design a modern zDevOps process
Notes: Intro’s first
About me …
My goals:
  Short-term - Help you navigate options that best fit your needs and current practices
  Work with your team to buildout a working pipeline (MVP)
  Recommend industry best practices and guidance to fit your needs

## Slide 3: Pilot / POC – ‘what to expect’
Assist your team to install and config. your DevOps software stack
Design Git Repos and a basic branching strategy
Migrate application(s) to git
Document and run ‘Use Cases’ for your ‘Doc. of Understanding’
Provide virtual hands-on training throughout the way
IBM provides this services free of charge
Pilots last ~ 3-4 months – and are more production ready
POCs ~ 1-2 MVP
Notes: How a POC is performed
Diff between POC/Pilot

## Slide 4
Milestone 1 - Software setup (1-2 weeks)
Milestone 2 - Configuration and IVP (1 week)
  Work with the DevOps team to define a Git Repo, your pipeline and DBB/Git configurations and scripts.
Milestone 3 - Design & Discovery
  Working sessions to help define the DOC, Use Cases and timelines.
Milestone 4 - Application Migration (2-3 days)
Milestone 5 - Run Use Cases Until Successful
Wrap-up
  Lesson’s learned
  Plan your next steps
Getting Started:
Assign a point person on your side to help arrange weekly meetings and track status, issues and milestones.
Define the system Admins, DevOps and Application Team(s) member who will support this engagement.
Review our DOU to clarify and agree on expectations for this pilot

## Slide 5: Session 1: Outline - Where are you today?
Mainframe Development:
Generally describe the mainframe development lifecycle from impact analysis to deployment.
Describe your basic system designs (mainframe, distributed and/or a mix, IMS, CICS …) high-level
App design and interfaces. Are they mostly via data (DB2, MQ, files), static and or dynamic calls or evenly mixed
How do you manage cross application impacts when sharing Common source (copybooks…)
Do you have clear application ownership
Describe
  testing strategy
  Hot fix flows
  Quality assurance
  Audit and Compliance requirements
Current Distributed Workflows
Repo design practices, Git Flows and branching, Pipelines design and restrictions, PR process, approvals, release management.
Current State Tools: ie – Git Hub, Jenkins, IDz, Deploy Tool, Artifactory/Nexus, Jira, Endevor/Changeman …
Security Model: Review your current practices Server access- RACF/ACF2, HTTPS/SSH to Git, Jenkins and z/OS
User access - Active Directory or other
Notes: NOTE: If the client responded to our questionnaire then this become more of a review and fine tuning of our understanding. Otherwise, let them explain their sdlc (m/f & Dist)
This is a presentation by the customer 60-90 minutes on current workflow
Start with Mainframe workflows and End with Distributed overview or held as a separate session

## Slide 6
What problem(s) are you trying to solve?
Concerns?
Timeframes?
Special processing – ie in-house preProcessors?
Anything else?

## Slide 7: Session 2 - IBM’s zDevOps Overview
DBB Arch Overview
Scripting framework (zAppBuild)
Git For Mainframe Development
  Review a generic git Flow design
  repo structure for mainframe apps
Workflows
  Migration – from PDS to GIT
  Day in the life of a developer
  Pipelines flows. From Pull Request to Publishing
Notes: IBM to present and discuss current zDevOps arch, tools and concepts ~60-90 using standard DBB/Git/UCD deck

## Slide 8: Session 3 – Proposed End-State Review
Build Flows
  Developer
  Pipeline
Git Repo Structures
  Application scope of a repo
  Structure and content (Folders/ Content)
  DBB Source code migration and initialization
  Managing Cross Application dependencies (multi-repo)
Branching Models (master, release, dev, feature)
Publishing DBB Output Artifacts
Approvals, Audit Trails and Best practices
Managing and maintaining new DevOps Framework (infra. as code)
Notes: IBM Presents – key areas for discovery is finding the right repo and git flow designs (A diagram would be great)
The final end-state recommendations will be provided a findings doc toward the end of the engagement
This is presented toward the end of the engagement.